| Climate Change and Sustainability action plan October 2026 Sustainability Lead – Vicky Lomas Review date: July 2027 |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Vision and Goals Vision: To create a sustainable, eco-conscious school environment that educates and empowers students, staff, and the wider community to take meaningful climate action. Goals: 1. Reduce the school’s carbon emissions by 30% by 2028. 2. Improve climate literacy across all grade levels. 3. Engage the whole school community in climate action. 4. Embed sustainability into school culture and operations. |  |  |  |
| Focus area | Goals | Actions | Timescale or expected completion date | Resources |
| Energy Use and Emissions | •Understand school’s carbon footprint by identifying where your emissions come from • Audit current energy use. • Reduce energy consumption and transition to renewable sources. • Promote anti-idling campaign. • Students to walk to work experience/local trips. • Reduce emissions and see improvement in Display Energy Certificate. | •Use an online tool such as Keep Britain Tidy’s to get a breakdown of carbon emissions. • Install solar panels (look for available grants) • Replace old lighting with LED bulbs. • Create an “Energy Monitors” student group •Encourage parents to turn off engines at pick up and drop off times •Install new boilers and water heaters in plant room | February 2027 Ongoing Ongoing Ongoing April 2027 | Count Your Carbon - Eco Schools (eco-schools.org.uk) https://www.gov.uk/government/publications/sustainability-and-climate-change-strategy https://letsgozero.org/impact/ https://www.transform-our-world.org/get-involved/resources/anti-idling-campaign |
| Waste Reduction | • Reduce landfill waste by 50%. • Encourage reuse, recycling, and composting. • Reduce printing of unnecessary documents. | • Launch a composting initiative for cafeteria waste. • Host a “Zero Waste Week” campaign. • Reduce the use of plastic cups in school • Student council to conduct checks on recycling within school • Run a uniform event at school for second hand uniform exchange and purchase. • Set up print codes for each class | Ongoing Ongoing July 2027 February 2027 | https://www.transform-our-world.org/get-involved/resources |
| Water Conservation | • Decrease water usage by 25%. | • Install water-saving devices in bathrooms and kitchens • Raise awareness about water usage through posters and assemblies | Ongoing Ongoing | https://www.wwf.org.uk/what-can-i-do/top-ten-water-saving-tips |
| Sustainable Transportation | • Reduce single-car school trips by 40%. | • Promote “Walk, Bike, or Bus to School” weeks. • Promote Cycle to work scheme. • Provide secure bike racks. | Ongoing | https://www.cyclescheme.co.uk/employer-registration/details |
| Green Spaces and Biodiversity | • Increase green spaces and improve biodiversity on campus. | • Set up insect hotels and bird feeders. • Use green space for outdoor learning. | July 2027 Ongoing |  |
| Climate Education and Student Leadership | • Make climate education a cross-curricular priority. • Empower student leaders. | • Integrate climate topics into science, geography, literature, and social studies. • Create a Student Climate Council. • Organize Earth Day events and student-led campaigns | Ongoing July 2027 Ongoing | https://www.transform-our-world.org/get-involved/resources |

- All classrooms now have a green recycling bin to recycle paper, cardboard and plastics. These are emptied weekly by students.

- There is a food waste bin for all kitchen waste.

- Uniform swap shop held July 2026.

- Anti-idling signs up in school car park. Regular reminders sent to parents.