|  | Action | Strategies | Person Responsible |
| --- | --- | --- | --- |
| Governance and community engagement | - Appoint a sustainability lead in line with expectations from DfE - Create a green wellbeing team - Setup an inclusive climate committee | - Teachers, TA’s, pupils, parents; involve emotional health champions - Draw on pupil led design principles |  |
| Baseline auditing and mapping | - Monitor energy use on a regular basis - Set BMS/BES appropriately over weekends, school holidays etc. - Map therapeutic outdoor spaces | - Through platforms such as Energy Sparks - Think about when the building will not be in use - Blend SEMH and environment goals e.g. calm corners doubling as biodiversity zones |  |
| Awareness and curriculum integration | - Take part in a switch off campaign - Education around recycling - Raise awareness around water consumption | - ‘Switch off fortnight’ aim for 10% reduction - As part of assemblies ‘Young Climate Warriors’ or carry out a waste audit (Waste Busters) |  |
| Quick wins | - Switch to LED lightbulbs - Install a smart meter - Run active travel campaigns - Increase meat-free offer - Check water meter for leaks | - Contact energy providers for a free consultation - Promote walking/biking to school - Meat-free Mondays every week |  |

YEAR 1 – Build foundations and awareness

YEAR 2 – Embed and expand

|  | Action | Strategies | Person Responsible |
| --- | --- | --- | --- |
| Decarbonisation and infrastructure | - Install renewables (solar/heat pumps) - Achieve 30% energy reduction - Apply for DfE’s climate action grants | - Use reinvested savings/grants - Relative to the Year 1 baseline - If eligible |  |
| Resilience and adaptation | - Add shade trees, and rain gardens to assess heat/flood risk - Build a dedicated ‘climate calm space’ | - Write a heatwave policy that addresses areas such as; school dress code, passive ventilation, and sun cream. Consider adopting the ‘Joint Union Heatwave Protocol’ - For pupils who suffer with climate related anxiety |  |
| Educational excellence | - Seek eco-schools green flag - Deliver a pupil-led climate/well-being event - Publish a green+ well-being report | - Expanding across the 7 themes - Invite families and council members - Celebrate achievements and next steps |  |
| Community leadership | - Lead a network of local SEMH schools - Collaborate with local councils - Apply for the national ‘Green Schools Alliance’ me | - Use Southwark/Ealing resources - Membership and awards |  |

YEAR 3 – Innovate and lead

|  | Action | Strategies | Person Responsible |
| --- | --- | --- | --- |
| Energy and buildings | - Improve insulation - Investigate small scale renewables - Install energy monitor displays | - Install window draft strips - Solar panels, air-source heat pump - In calm zones |  |
| Grounds and biodiversity | - Establish a gardening/nature club - Start student-led wildlife surveys at break times | - Sensory planting, use green light trust model for woodland planting - Explore and observe what wildlife is on the school grounds already - Register school with RHS Campaign |  |
| Waste, water and consumption | - Launch termly ‘eco-wellbeing challenges’ - Enhance recycling and water use monitoring | - Set up an eco-club for pupils to take leadership - Water-butts in the garden to use rainwater for watering plants. - Automatic taps |  |
| Curriculum and engagement | - Integrate climate projects into SEMH support - Register with The Nature Park (NENP) - Access the Climate Ambassadors Scheme | - Growing foods and reflection zones - Embed nature based learning, encourage young people to improve their site for wildlife and people - Invite the climate ambassadors to school to do an assembly on a topic of interest |  |

Monitoring and evaluation

- Termly track energy, waste, water, and travel

- Conduct pupil and staff surveys on wellbeing and environmental confidence

- Annual publication of progress and next-year goals

- Celebration events each year, including sensory garden showcase and awards

- Add to termly school council agenda

SEMH Links

- Integrates well-being and nature: outdoor learning supports emotional regulation

- Inclusive, trauma informed design: calm corners double as learning zones

- Practical, sensory engagement: plants, compost, and tools give hands-on support

- Peer and community support: builds confidence and civic agency

- Clear, achievable steps: avoids overwhelm, celebrates progress