School Improvement Plan

2024 - 2025

Vision and Values

Heaton School is all about preparing our young people for adulthood.

Our 4 word ethos is:

ENJOY

We want all learning to be enjoyable

CHALLENGE

We want our students to be challenged to develop key skills and abilities in readiness for living their everyday lives

CELEBRATE

We want to celebrate diversity across the school

ACHIEVE

We want all students to achieve great things

LEADERSHIP AND MANAGEMENT

| 1.1 Introduction of Pathway leader role 1.2 Implementation of pathway(s) curriculum |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Milestones | Date | Responsibility | Outcomes | Update/ evidence | Status (R/A/G) |
| 1.1 | Pathway leaders to develop in their roles to ensure effective management of all pathways | July 2025 | HT/DHT | Effective management of pathway curriculu | Pathway leader meetings 4/25 – completed pathway report covering attendance/ behaviour/ Pupil Premium/ attainment information – will help to inform future SDP |  |
| 1.2 | Pathway leaders to work alongside DHT to implement pathway curriculum for x3 areas integrating and adapting the EQUALS curriculum (see curriculum action plan) | July 2025 | DHT/ Pathway leaders | Improved curriculum offer for all students | Pathway reports Curriculum policies Pathway intent statements Class intent statements 9/24 – Class intent statements written 1/25 – Curriculum policies reviewed inline with EQUALS curriculum 1/25 – Decision made to merge formal curriculum with semi formal 4/25 – Trial set for semi formal curriculum in summer term in readiness for September |  |
| 1.3 Improved pedagogical understanding across all curriculum areas |  |  |  |  |  |  |
| 1.30 | Teachers to research x2 pedagogical theories and practice in relation to their pathway and/or curriculum area – linking in with Rosenshine Principles of learning | May 2025 | All Teachers | Improved pedagogical understanding around teaching – in relation to cohort of learners – this will help to improve standards of teaching and learning | PD overview 1/25 – Teacher PD programme started 3/25 – All PD groups focussed on Rosenshine principles of learning/ relevant research |  |
| 1.31 | Paired / peer coaching as part of assigned PD time in working week (teachers) | July 2025 | All Teachers | As above | 4/25 – As above - Evaluation required? |  |
| 1.4 Review School Safeguarding processes |  |  |  |  |  |  |
| 1.40 | Revisit manual handling training policy and train x1 staff in academic year to roll out training throughout the school | Mar 2025 | HT | Manual handling training in line with policy and expected procedures | Certificate of training completion 1/25 – GF completed training |  |
| 1.41 | Introduce checks at the start of the day for students equipment – including sling checks | Dec 2024 | HT | Improved awareness and understanding of student safety | Equipment Check PRO FORMA Introduced 10/24 – AUDIT REQUIRED |  |
| 1.5 Improved Performance Management processes |  |  |  |  |  |  |
| 1.50 | Trial Rossenshine learning walks/ focus – linked to teachers Personal development time | Feb 2025 | HT | Improved teaching and learning/ learning outcomes | Learning walk summary/ individual feedback sheets 2/25 – Learning walk completed – Focus in round 1 on scaffolding of learning, modelling and daily review |  |
| 1.6 Review school policies and associated processes |  |  |  |  |  |  |
| 1.60 | Review and rewrite school policy schedule | Dec 2024 | HT | Improved and updated school policies in line with government / DFE guidance and expectations | FGM reports/ minutes Completed policies – see website 4/25 - Updates completed for: Safeguarding AUP Whistleblowing Business continuity Curriculum Assessment On target to update all essential policies by the end of the academic year |  |
| 1.7 Governance – increase in accountability for school performance – Behaviour, attendance, achievement/ attainment |  |  |  |  |  |  |
| 1.70 | Write and implement Data strategy to report back to Governor’s in meetings | Dec 24 | HT | Improved strategic data collection to inform school development/ prioritise planning | Data strategy still requires completion Pathway reports 4/25 – Pathway report trial completed 4/25 – AR and RM met with EFL to discuss ways to meaningfully present data using insights / pertaining to IEP target acquisition |  |
| 1.71 | Introduce improved ways for Governors to know, appreciate and challenge curriculum developments/ quality of provision within school | July 25 | HT | Improved accountability for leaders across the school | Meeting minutes Reports from conversations Pathway reports 10/24 – Governors assigned to pathways/ priority subject areas 1/25 – Strategic monitoring group established 4/25 – x1 monitoring group completed – HT discussed pathway curriculum and its merits/ key developments |  |
| OTHER |  |  |  |  |  |  |
| 1.80 | Review and rewrite school website in line with guidelines and curriculum changes | July 25 | SLT/ IT support/ SBM | Improved understanding of school ethos/values/ direction/ purpose | Website action plan Ofsted compliance check 12/24 – ofsted compliance check completed (MM) 3/25 – Phase 1 completed – all curriculum information is now correct |  |
| 1.81 | Explore income generation opportunities for school | Apr 25 | SBM/ HT | Help to improve budget status | 10/24 – Forest school clubs - weekends | ongoing |
| 1.82 | To increase school bank staff to reduce / eradicate use of agency | Mar 25 | SBM/HT | Improved consistency in staffing across the school | 4/25 - Increased bank staff by x2 staff | ongoing |
| 1.83 | To write a 5 year maintenance and replacement plan for school ICT infrastructure |  | SBM/HT | Improved access to updated ICT across school | 3/25 -writing plan in relation to work with LA around school infrastructure developments/ project |  |
| 1.84 | To write a 5 year maintenance school building plan |  | SMB/HT | Improved teaching facilities across school | 4/25 – potential LA investment /development? |  |
| 1.85 | To plan for redevelopment of outdoor/ play areas |  | PTA / HT/ SBM | Improved play opportunities for students | As above |  |

QUALITY OF EDUCATION

| 2.1 Sequential curriculum across all pathways |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Milestones | Date | Responsibility | Outcomes | Comment/ update | Status (R/A/G) |
| 2.10 | Re write current schemes for Pre-formal / formal pathways | July 25 | DHT / Pathway leads | Improved coherent planning for pre formal and formal students | Examples of planning/ schemes of work 11/24 – Formal pathway merged with semi formal after initial review 2/25 – Preformal EQUALS curriculum purchased 4/25 - Preformal curriculum rewritten in readiness for summer trial 4/25 – Semi formal curriculum rewritten in readiness for summer term trial |  |
| 2.11 | Adapt Equals curriculum for Informal and semi formal curriculum | May 25 | DHT/ Pathway leaders | Improved curriculum offer for informal and semi formal students | As above – informal curriculum continually being reviewed working closely with pathway lead |  |
| 2.12 | Teacher PD sessions introduced with pedagogical focus around sequential learning | Nov 24 | HT/ Teachers | Improved staff understanding of pedagogical thinking | 3/25 – first trial completed |  |
| 2.13 | Full review of maths curriculum for all 4 pathways – review will lead to rewrite in line with EQUALS curriculum | July 25 | Maths leader(s) | Improved sequential learning in maths | Maths policy Maths SOW 3/25 - Curriculum leaders attended training and liaised with other schools who have adopted the EQUALS curriculum Draft policy completed |  |
| 2.14 | Review and rewrite ‘The World around me’ curriculum using the EQUALs framework (relevant to all 4 pathways) | July 25 | Subject leader | Improved curriculum for students to understand the world they live in | World around me policy World around me SOW |  |
| 2.15 | Review RSE and PSHCE curriculum and relevance to pathway model | July 25 | Subject leader | Up to date and relevant learning for students in PSHCE and RSE | 2/25 – SOW/ content reviewed in relation to EQUALS curriculum – discussion had in relation to masturbation behaviour and suitability of curriculum for Heaton cohort 3/25 – Curriculum lead met with all pathway leaders to plan around students needs |  |
| 2.16 | Adapt current curriculum planning (previous core) for formal curriculum to ensure that LO’s are sequential and meaningful | 31/12/2024 | AHT | Improved formal pathway offer | Formal pathway now merged with Semi formal |  |
| 2.2 4 word ethos embedded throughout the curriculum |  |  |  |  |  |  |
| 2.20 | Write Class intent statements to determine clear curriculum intent using the 4 words | 30/09/2024 | DHT | Improved understanding of 4 word ethos | Intent statements completed and posted onto doors |  |
| 2.21 | Introduce 4 word ethos plenaries within lessons – celebration boards | 31/12/2024 | AH | SLT should be able to identify the positive impact of the recent training and ongoing development across the school. | 1/25 – celebration boards in ALL classrooms – evidence of students work/ progress linked to all 4 words |  |
| 2.3 Reading to be meaningfully embedded throughout the school curriculum |  |  |  |  |  |  |
| 2.30 | Introduce a school library space to promote reading within school | July 2025 | HT/ English lead | Improved access/ promotion of reading for pleasure | 10/24 – Funding obtained for reading materials 11/24 – Plans in place for developing reading area 2/25 – Plans for area to be in place for summer 2 – all books purchased |  |
| 2.31 | Texts to have coverage for all curriculum areas and pathways – consideration to diversity – cultural etc | April 2025 | DHT/ Pathway leaders/ subject leaders | Students have Improved access to diverse texts within school | 2/25 - Books purchased using grant - diverse range of themes and they promote diversity/ wider cultural understanding |  |
| 2.32 | Introduce reading rope/ model throughout school | July 2025 | English leads | Shared understanding throughout school of the importance of reading and how it applies to Heaton students |  |  |
| 2.40 | All SEND phonics training completed by support staff (TA’s) | Sep 2024 | HT/ English lead | Staff readiness to teach SEND phonics programme | Completed 9/25 |  |
| 2.41 | Timetabled Phonics sessions in semi-formal and formal pathways | Nov 2024 | English lead/ DHT |  | Timetables Observation records ?? |  |
| 2.42 | Observation of practice working with SEND phonics team | May 2025 | English lead(s) |  |  |  |
| 2.5 Review and implement effective school assessment and reporting processes |  |  |  |  |  |  |
| 2.50 | Refocus all assessment using IEP as focus – H levels to be discontinued | Dec 2024 | AHT | Improved/ simplified assessment processes | 9/24 – Full staff training – SMART target setting / IEP’s 11/24 – IEP audit – feedback given out to staff 2/25 – Introduction of Proof of Progress meetings (POP) – trial and review in readiness for 9/25 | On track |
| 2.51 | SCERTS assessment framework – trialled with informal pathway | Dec 2024 | AHT | Improved assessment processes to identify learning outcomes | 10/24 – Inf leader attended SCERTS training – fedback to SLT 11/24 – Working group setup to focus on SCERTS appropriateness for Heaton learners 12/25 – MAPP linked to EQUALS and overlap with SCERTS framework – revert to focussing on MAPP trial this year |  |
| 2.52 | SCERTS assessment framework – implement across relevant pathways | July 2025 | AHT/ DHT |  | See above |  |
| 2.56 | Source English/ maths assessment tool matched to revised curriculum for Semi formal and formal pathways | Jul 2025 | AHT/DHT |  | More work needed on this area |  |
| 2.57 | Implement new maths and English assessment tool | July 2025 | DHT/AHT |  | Summer focus needed |  |
| 2.58 | Trial MAPP assessment tool for 14-19 students | July 2025 | DHT/AHT |  | 2/25 – Trial started with sample of teachers across informal and semi formal pathways |  |
| 2.6 Subject specialism training/CPD for subject leaders |  |  |  |  |  |  |
| 2.60 | Introduce PD time for teachers – 1 hour per week | Nov 2024 | HT | Improved professional development of teachers to raise improvement in student outcomes | Completed |  |
| 2.61 | Teachers to network and/or attend subject related training/ activity | July 25 | HT | Raise expertise in subject leaders to improve learning outcomes for students | Training records Appraisal documentation 10/24 – Appraisal meetings held 11/24 – Teachers visited outstanding SEND provision as part of Nov inset day - fed back findings to team (Twilight session) |  |
| 2.62 | DEAL training to be completed by lead teacher and disseminated to staff team | July 25 | Perf arts lead/ SLT | Improved student offer | 4/25 - LW attended x2 sessions Overlap into 25/26 – full training delivered to team as part of full staff inset (April 26) |  |
| 2.63 | Omni music practitioners to work alongside teacher team to develop music strategies /interwoven into the pathway curriculum | July 25 | Creative and perf arts leaders | Improved student offer | Podcast recording Evidence/ documentation of sessions Ongoing work alongside omni practioners 4/25 – staff training planned in summer term for rolling out sounds of intent assessment framework 25/26 |  |

BEHAVIOUR AND ATTITUDES

| 3.1 Review PBS/ behaviour management training for support and care staff |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Milestones | Date | Responsibility | Outcomes | Comment | Status (R/A/G) |
| 3.10 | Develop training opportunities for school support staff to improve in their understanding and support of challenging behaviour | Feb 25 | HT/ Student support manager | Improved support of behaviour in school | 4/25 – Full staff training delivered in IRIS reporting, PBS approach, scenario led training |  |
| 3.11 | Train x1 staff members in Team TEACH train the trainer | Jul 25 | HT | Enables strategic planning of Team TEACH training from 25/26 | Completed – AW completed course in 3/25 |  |
| 3.12 | Expansion of student support team to improve support during the school day | Dec 24 | SLT/ Student support Manager | Improved support of students throughout the school day | Additional member in place – due to staffing issues/ S and A impact limited at present |  |
| 3.2 Behaviour reporting to inform all staff of behaviour trends and interventions across school |  |  |  |  |  |  |
| 3.20 | Review use of iris for behaviour reporting | Nov 24 | SLT/ Student support Manager | Improved day to day understanding of behavioural presentation | 10/24 – met with IRIS to revise reporting protocols/ process 12/24 – training rolled out for all new staff and refreshers throughout autumn and spring term |  |
| 3.21 | Create behaviour/trend data report (using IRIS) to share with staff team at set points throughout the term | Dec 24 | SLT/ Student support Manager | Ensure that staff can proactively react to behavioural trends to raise improvement | Termly behaviour reports 4/25 – reports have informed pathway leaders in writing pathway reports for spring term |  |
| 3.22 | Realign behaviour reporting to pathway model | Dec 24 | Student support Manager | Improved reporting to inform practice in classes | As above |  |
| 3.23 | Introduction of RPI debrief as part of daily routine | Mar 25 | Student support Manager | Minimising reoccurrence of RPI in future | 3/25 - Debriefs have been trialled and positive feedback from staff |  |
| 3.3 Student support offer – develop interventions on offer to students |  |  |  |  |  |  |
| 3.30 | Staff to train in lego therapy and trial intervention sessions | Jul 25 | HT/ Student support team | Improved intervention offer |  |  |
| 3.31 | Trial restorative practice techniques to resolve student-student issues where applicable | Jul 25 | Student support team | Improved intervention offer |  |  |
| 3.4 Maintenance of good behaviour management practice throughout school |  |  |  |  |  |  |
| 3.40 | Introduction of class debrief / supervision | Mar 25 | HT | Allows staff to reflect on practice to ensure consistency is maintained and issues addressed | Informal debriefs have been established – not currently part of regular routine? |  |

PERSONAL DEVELOPMENT

| 4.1 Continue developing strong external and internal work experience to enhance careers provision. 4.2 Continue to maintain links with Greater Manchester Combine Authority Enterprise Co-ordinator to utilise support and resources to work towards meeting Gatsby Benchmarks and enhance CIAG and WRL offer in school. 4.3 Appoint Careers advisor |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Milestones | Date | Responsibility | Outcomes | Comment | Status (R/A/G) |
| 4.10 | DHT to train designated member of staff to further develop work experience opportunities for post 16 students | July 25 | DHT | Improved management of work based learning/ experience | 4/25 - Scope to assign Terrie? |  |
| 4.20 | DHT to attend relevant network events where applicable | July 25 | DHT |  |  |  |
| 4.30 | Appoint careers advisor to support students and advise throughout the school | Mar 25 | DHT/HT | Improved student careers offer | 3/25 – Completed – in recent SLT meeting DHT raised concern that advisor is not meeting the needs of students effectively – will need to review input going forward |  |
| 4.4 Create opportunities for more encounters with further education providers |  |  |  |  |  |  |
| 4.40 | AS 4.20 |  |  |  |  |  |
| 4.5 Develop extracurricular offer for the school. |  |  |  |  |  |  |
| 4.50 | Develop partnership with forest school provider (external) | May 2025 | SBM/ HT |  | 4/25 - Ongoing work with external forest school provider – exploring scope for after school/ holiday provision? | Ongoing |
| 4.51 | Work in partnership with Progressive sports coaching to train staff and develop SEND sports holiday provision | July 2025 | SBM/HT |  |  |  |
| 4.6 Review equality & diversity/ SMSC strategy in school |  |  |  |  |  |  |
| 4.60 | Create E and D calendar in line with review of Religious education strategy | July 2025 | SLT |  |  |  |
| 4.61 | Review corporate worship and school assembly policy | July 2025 | SLT/ pathway leaders |  |  |  |
| 4.7 Develop community cohesion strategy across school |  |  |  |  |  |  |
| 4.70 | Staff to receive anti racism / community cohesion training | Mar 2025 | HT | Improved school / community cohesion | 4/25 – x3 sessions delivered by E and D staff member as part of full staff CPD offer |  |
| 4.71 | Strategy devised to ensure that community cohesion is effectively weaved into the curriculum | July 2025 | HT/DHT/ Pathway leaders |  |  |  |
| 4.8 Review anti bullying strategy across school |  |  |  |  |  |  |
| 4.80 | Ensure anti bullying message is woven into the PSHE curriculum – relevant to all 4 pathways | July 2025 | HT/ PSHE lead/ DHT |  |  |  |
| 4.81 | Review anti bullying policy | July 2025 | SLT |  |  |  |